## Sheet1
[8 empty] | MTBD |  | FARM |  | AD
So.No | Apis URL | VERB | MTBD | FARM | AD | Start Date | End Date | Status | Envoirement | Status | Envoirement | Status | Envoirement | Comments
1 | /login | Post | Yes | Yes | Yes | 2017-05-08 | 2017-05-10 | Done | Hosted on UAT | Done | PreUAT | Done
2 | /ForgotPassword | Post | Yes | Yes | Yes | 2017-05-08 | 2017-05-09 | Done | Hosted on UAT | Done | PreUAT | Done
3 | /resetpassword | Post | Yes | Yes | Yes | 2017-05-10 | 2017-05-12 | Done | Hosted on UAT | Done | PreUAT | Done
4 | /changepassword | Post | Yes | Yes | Yes | 2017-05-11 | 2017-05-12 | Done | Hosted on UAT | Done | PreUAT | Done
5 | Testing |  | Yes | Yes | Yes | 2017-05-08 | 2017-05-15
6 | /listVehicles | Get | Yes | Yes | Yes | 2017-05-15 | 2017-05-16 | Done | Hosted on UAT | Done | PreUAT | in progress |  | We need clarification for few farm API s' Response from client and uma sir
7 | /listVehicles/mtbd | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
8 | /listVehicles/farm | Get | No | Yes | No | 2017-05-15 | 2017-05-16 | Not Required |  | Done | PreUAT | Not Required
9 | /listVehicles/AD | Get | No | No | Yes | 2017-05-16 | 2017-05-17 | Not Required |  | Not Required |  | in progress
10 | /vehiclesSummary/{vehicleregno} | Get | Yes | Yes | Yes | 2017-05-17 | 2017-05-19 | Done | Hosted on UAT | Done | PreUAT | in progress
11 | /liveVehicleInformation/{vehicleregno} | Get | Yes | Yes | Yes | 2017-05-17 | 2017-05-19 | Done | Hosted on UAT | Done | PreUAT | in progress
12 | /vehicles/{vehicleregno}/dealers | Get | Yes | No | Yes | 2017-05-22 | 2017-05-23 | Done | Hosted on UAT | Not Required |  | Not Yet Started
13 | UAT Testing |  | Yes | Yes | Yes | 2017-05-15 | 2017-05-23 |  |  |  |  | Not Yet Started
14 | /vehicleAlerts | Get | Yes | Yes | Yes | 2017-05-22 | 2017-05-24 | Done | Hosted on UAT | Done | PreUAT | Not Yet Started
15 | /vehicleAlerts/vehicleAlerts/{vehicleRegNo} | Get | Yes | Yes | Yes | 2017-05-24 | 2017-05-26 | Done | Hosted on UAT | Done | PreUAT | Not Yet Started
16 | /breakDown/{vehicleRegNo} | Put | Yes | No | Yes | 2017-05-25 | 2017-05-26 | Done | Hosted on UAT | Not Required |  | Not Yet Started |  | Need to ask to uma sir because it is given in SOR 11 for Farm
17 | UAT Testing |  | No | Yes | Yes | 2017-05-26 | 30/5/2017 |  |  |  |  | Not Yet Started
18 | /expense/{vehicleRegNo} | Put | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
19 | /expense/{vehicleRegNo} | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
20 | /expenseCategory/{vehicleRegNo} | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
21 | /reportSummary/platform/{platform}/health | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
22 | /reportSummary/platform/{platform}/status | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
23 | /locationHistory/{vehicleRegNo} | Get | Yes | Yes | Yes | 2017-05-29 | 2017-05-30 | Done | Hosted on UAT | Done | PreUAT | Not Yet Started
24 | UAT Testing |  |  |  |  | 2017-05-31 | 2017-05-31
25 | /driverprofiles | Get | Yes | No | Yes | 2017-05-29 | 2017-05-30 | Done | Hosted on UAT | Not Required |  | Not Yet Started
26 | /driverprofiles/driver | Post | Yes | No | Yes | 2017-05-30 | 2017-05-31 | Done | Hosted on UAT | Not Required |  | Not Yet Started
27 | /driverProfiles/{driverId} | Get | Yes | No | Yes | 2017-05-31 | 2017-05-31 | Done | Hosted on UAT | Not Required |  | Not Yet Started
28 | /driverprofiles/driverProfiles/{driverId} | Patch | Yes | No | Yes | 2017-06-01 | 2017-06-01 | Done | Hosted on UAT | Not Required |  | Not Yet Started
29 | /driverprofiles/driverProfiles/{driverId} | Delete | Yes | No | Yes | 2017-06-01 | 2017-06-02 | Done | Hosted on UAT | Not Required |  | Not Yet Started
30 | /profile | Get | Yes | Yes | Yes | 2017-06-02 | 2017-06-05 | Done | Hosted on UAT | Done | PreUAT | Not Yet Started
31 | /profile | Patch | Yes | Yes | Yes | 2017-06-05 | 2017-05-07 | Done | Hosted on UAT | Done | PreUAT | Not Yet Started
32 | /vehicleMappingWithDriver/{vehicleRegNo}/{driverId} | Post | Yes | No | Yes | 2017-06-07 | 2017-06-08 | Done | Hosted on UAT | Not Required |  | Not Yet Started
33 | /driverProfiles/{driverId}/idProof | Get | Yes | No | Yes | 2017-06-08 | 2017-06-09 | Done | Hosted on UAT | Not Required |  | Not Yet Started
34 | /vehicleMappingWithDriver/{vehicleRegNo} | Post | Yes | No | Yes | 2017-06-09 | 2017-06-12 | Done | Hosted on UAT | Not Required |  | Not Yet Started
35 | UAT Testing |  |  |  |  | 2017-06-12 | 2017-06-05
36 | /geofence | Post | Yes | Yes | Yes | 2017-06-01 | 2017-06-05 | Done | Hosted on UAT | Done | PreUAT | Not Yet Started |  | Done but Geofence Validation need to ask discuss with Uma Sir. It is paid api of google
37 | /geofence | Get | Yes | Yes | Yes | 2017-06-05 | 2017-06-07 | Done | Hosted on UAT | Done | PreUAT | Not Yet Started
38 | /geofence/{name} | Patch | Yes | Yes | Yes | 2017-06-07 | 2017-06-09 | Done | Hosted on UAT | Done | PreUAT | Not Yet Started |  | Done but Geofence Validation need to ask discuss with Uma Sir. It is paid api of google
39 | /geofence/{name}/vehicles | Put | Yes | Yes | Yes | 2017-06-12 | 2017-06-13 | Done | Hosted on UAT | Done | PreUAT | Not Yet Started
40 | /geofence/{name} | Delete | Yes | Yes | Yes | 2017-06-12 | 2017-06-14 | Done | Hosted on UAT | Done | PreUAT | Not Yet Started
41 | /geofence/vehicles | Get | Yes | Yes | Yes | 2017-06-14 | 2017-06-15 | Done | Hosted on UAT | Done | PreUAT | Not Yet Started
42 | /geofence/{name}/vehicles | Get | Yes | Yes | Yes | 2017-06-15 | 2017-06-16 | Done | Hosted on UAT | Done | PreUAT | Not Yet Started
43 | UAT Testing |  |  |  |  | 2017-06-16 | 2017-06-19
44 | /reportSummary/platform/mtbd | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
45 | /reportSummary/platform/farm | Get | No | Yes | No | 2017-06-16 | 2017-06-16 | Not Required |  | Done | PreUAT | Not Required
46 | /reportSummary/platform/AD | Get | No | No | Yes | 2017-06-19 | 2017-06-19 | Not Required |  | Not Required |  | Not Yet Started
47 | /report/platform/mtbd/vehiclemovement/speeddata/{vehicleRegNo} | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
48 | /report/platform/mtbd/vehiclemovement/usagetime/{vehicleRegNo} | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
49 | //report/platform/mtbd/vehiclemovement/enginerpm/{vehicleRegNo} | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
50 | /report/platform/mtbd/vehiclemovement/vehiclemovementsummary/{vehicleRegNo} | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
51 | /report/platform/mtbd/vehiclemovement/vehiclemovementreport/{vehicleRegNo} | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
52 | /report/platform/mtbd/delivery/vehicleusage/{vehicleRegNo} | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
53 | /report/platform/mtbd/alerts/vehiclealerts/{vehicleRegNo} | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
54 | /report/platform/mtbd/alerts/violation/{vehicleRegNo} | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
55 | /report/platform/mtbd/alerts/alertssummary/{vehicleRegNo} | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
56 | /report/platform/mtbd/vehiclehealth/vehiclehealthsummary/{vehicleRegNo} | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
57 | /report/platform/mtbd/delivery/vehicleusagesummary/{vehicleRegNo} | Get | Yes | No | No |  |  | Done | Hosted on UAT | Not Required |  | Not Required
58 | /report/platform/farm/vehiclemovement/usagehours/{vehicleRegNo} | Get | No | Yes | No | 2017-06-19 | 2017-06-20 | Not Required |  | Done | PreUAT | Not Required
59 | /report/platform/farm/vehiclemovement/vehicleutilization/{vehicleRegNo} | Get | No | Yes | No | 2017-06-20 | 2017-06-20 | Not Required |  | Done | PreUAT | Not Required
60 | /report/platform/farm/vehiclemovement/enginehours/{vehicleRegNo} | Get | No | Yes | No | 2017-06-21 | 2017-06-22 | Not Required |  | Done | PreUAT | Not Required
61 | /report/platform/farm/alerts/vehiclealerts/{vehicleRegNo} | Get | No | Yes | No | 2017-06-21 | 2017-06-22 | Not Required |  | Done | PreUAT | Not Required
62 | /report/platform/farm/alerts/violation/{vehicleRegNo} | Get | No | Yes | No | 2017-06-22 | 2017-06-23 | Not Required |  | Done | PreUAT | Not Required
63 | UAT Testing |  |  |  |  | 2017-06-23 | 2017-06-27
Yes
No