## Sheet1
So.No | Apis URL | VERB | MTBD | FARM | AD | Start Date | End Date | Efforts | MTBD Status | Farm Status | AD Status | Comments
1 | /login | Post | Yes | Yes | Yes | 2017-05-08 | 2017-05-10 | 6 | Done | Done | Done
2 | /ForgotPassword | Post | Yes | Yes | Yes | 2017-05-08 | 2017-05-09 | 6 | Done | Done | Done
3 | /resetpassword | Post | Yes | Yes | Yes | 2017-05-10 | 2017-05-12 | 6 | Done | Done | Done
4 | /changepassword | Post | Yes | Yes | Yes | 2017-05-11 | 2017-05-12 | 6 | Done | Done | Done
5 | Testing |  | Yes | Yes | Yes | 2017-05-08 | 2017-05-15 | 8 | Done | Done | In Progress
6 | /listVehicles | Get | Yes | Yes | Yes | 2017-05-15 | 2017-05-16 | 0 | Done | Not Required | Not Required
7 | /listVehicles/mtbd | Get | Yes | No | No |  |  | 4 | Not Required | Done | Not Required
8 | /listVehicles/farm | Get | No | Yes | No | 2017-05-15 | 2017-05-16 | 4 | Not Required | Not Required | In Progress
9 | /listVehicles/AD | Get | No | No | Yes | 2017-05-16 | 2017-05-17 | 9 | Done | Done | In Progress
10 | /vehiclesSummary/{vehicleregno} | Get | Yes | Yes | Yes | 2017-05-17 | 2017-05-19 | 12 | Done | Done | Not Started
11 | /liveVehicleInformation/{vehicleregno} | Get | Yes | Yes | Yes | 2017-05-17 | 2017-05-19 | 9 | Done | Not Required | Not Started
12 | /vehicles/{vehicleregno}/dealers | Get | Yes | No | Yes | 2017-05-22 | 2017-05-23 | 9 | Done | Done | Not Started
13 | UAT Testing |  | Yes | Yes | Yes | 2017-05-15 | 2017-05-23 | 9 | Done | Done | Not Started
14 | /vehicleAlerts | Get | Yes | Yes | Yes | 2017-05-22 | 2017-05-24 | 9 | Done | Not Required | Not Started | But need to confirm with Uma Sir because it is given in SOR 11 for farm also
15 | /vehicleAlerts/vehicleAlerts/{vehicleRegNo} | Get | Yes | Yes | Yes | 2017-05-24 | 2017-05-26 | 0 | Done | Not Required | Not Required
16 | /breakDown/{vehicleRegNo} | Put | Yes | No | Yes | 2017-05-25 | 2017-05-26 | 0 | Done | Not Required | Not Required
17 | UAT Testing |  | No | Yes | Yes | 2017-05-26 | 30/5/2017 | 0 | Done | Not Required | Not Required
18 | /expense/{vehicleRegNo} | Put | Yes | No | No |  |  | 0 | Done | Not Required | Not Required
19 | /expense/{vehicleRegNo} | Get | Yes | No | No |  |  | 0 | Done | Not Required | Not Required
20 | /expenseCategory/{vehicleRegNo} | Get | Yes | No | No |  |  | 8 | Done | Done | Not Started
21 | /reportSummary/platform/{platform}/health | Get | Yes | No | No |  |  | 5 | Done | Not Required | Not Started
22 | /reportSummary/platform/{platform}/status | Get | Yes | No | No |  |  | 5 | Done | Not Required | Not Started
23 | /locationHistory/{vehicleRegNo} | Get | Yes | Yes | Yes | 2017-05-29 | 2017-05-30 | 5 | Done | Not Required | Not Started
24 | UAT Testing |  |  |  |  | 2017-05-31 | 2017-05-31 | 5 | Done | Not Required | Not Started
25 | /driverprofiles | Get | Yes | No | Yes | 2017-05-29 | 2017-05-30 | 5 | Done | Not Required | Not Started
26 | /driverprofiles/driver | Post | Yes | No | Yes | 2017-05-30 | 2017-05-31 | 15 | Done | Done | Not Started
27 | /driverProfiles/{driverId} | Get | Yes | No | Yes | 2017-05-31 | 2017-05-31 | 18 | Done | Done | Not Started
28 | /driverprofiles/driverProfiles/{driverId} | Patch | Yes | No | Yes | 2017-06-01 | 2017-06-01 | 6 | Done | Not Required | Not Started
29 | /driverprofiles/driverProfiles/{driverId} | Delete | Yes | No | Yes | 2017-06-01 | 2017-06-02 | 9 | Done | Not Required | Not Started
30 | /profile | Get | Yes | Yes | Yes | 2017-06-02 | 2017-06-05 | 6 | Done | Not Required | Not Started
31 | /profile | Patch | Yes | Yes | Yes | 2017-06-05 | 2017-05-07 | 18 | Done but Geofence Validation | Done but Geofence Validation | Not Started | Done but Geofence Validation need to ask discuss with Uma Sir
32 | /vehicleMappingWithDriver/{vehicleRegNo}/{driverId} | Post | Yes | No | Yes | 2017-06-07 | 2017-06-08 | 9 | Done | Done | Not Started
33 | /driverProfiles/{driverId}/idProof | Get | Yes | No | Yes | 2017-06-08 | 2017-06-09 | 18 | Done but Geofence Validation | Done but Geofence Validation | Not Started | Done but Geofence Validation need to ask discuss with Uma Sir
34 | /vehicleMappingWithDriver/{vehicleRegNo} | Post | Yes | No | Yes | 2017-06-09 | 2017-06-12 | 9 | Done | Done | Not started
35 | UAT Testing |  |  |  |  | 2017-06-12 | 2017-06-05 | 9 | Done | Done | Not started
36 | /geofence | Post | Yes | Yes | Yes | 2017-06-01 | 2017-06-05 | 6 | Done | Done | Not started
37 | /geofence | Get | Yes | Yes | Yes | 2017-06-05 | 2017-06-07 | 8 | Done | Done | Not started
38 | /geofence/{name} | Patch | Yes | Yes | Yes | 2017-06-07 | 2017-06-09 | 0 | Done | Not Required | Not Required
39 | /geofence/{name}/vehicles | Put | Yes | Yes | Yes | 2017-06-12 | 2017-06-13 | 5 | Not Required | Done | Not Required
40 | /geofence/{name} | Delete | Yes | Yes | Yes | 2017-06-12 | 2017-06-14 | 5 | Not Required | Not Required | Not started
41 | /geofence/vehicles | Get | Yes | Yes | Yes | 2017-06-14 | 2017-06-15 | 0 | Done | Not Required | Not Required
42 | /geofence/{name}/vehicles | Get | Yes | Yes | Yes | 2017-06-15 | 2017-06-16 | 0 | Done | Not Required | Not Required
43 | UAT Testing |  |  |  |  | 2017-06-16 | 2017-06-19 | 0 | Done | Not Required | Not Required
44 | /reportSummary/platform/mtbd | Get | Yes | No | No |  |  | 0 | Done | Not Required | Not Required
45 | /reportSummary/platform/farm | Get | No | Yes | No | 2017-06-16 | 2017-06-16 | 0 | Done | Not Required | Not Required
46 | /reportSummary/platform/AD | Get | No | No | Yes | 2017-06-19 | 2017-06-19 | 0 | Done | Not Required | Not Required
47 | /report/platform/mtbd/vehiclemovement/speeddata/{vehicleRegNo} | Get | Yes | No | No |  |  | 0 | Done | Not Required | Not Required
48 | /report/platform/mtbd/vehiclemovement/usagetime/{vehicleRegNo} | Get | Yes | No | No |  |  | 0 | Done | Not Required | Not Required
49 | //report/platform/mtbd/vehiclemovement/enginerpm/{vehicleRegNo} | Get | Yes | No | No |  |  | 0 | Done | Not Required | Not Required
50 | /report/platform/mtbd/vehiclemovement/vehiclemovementsummary/{vehicleRegNo} | Get | Yes | No | No |  |  | 0 | Done | Not Required | Not Required
51 | /report/platform/mtbd/vehiclemovement/vehiclemovementreport/{vehicleRegNo} | Get | Yes | No | No |  |  | 0 | Done | Not Required | Not Required
52 | /report/platform/mtbd/delivery/vehicleusage/{vehicleRegNo} | Get | Yes | No | No |  |  | 18 | Not Required | done | Not Required
53 | /report/platform/mtbd/alerts/vehiclealerts/{vehicleRegNo} | Get | Yes | No | No |  |  | 18 | Not Required | done | Not Required
54 | /report/platform/mtbd/alerts/violation/{vehicleRegNo} | Get | Yes | No | No |  |  | 18 | Not Required | done | Not Required
55 | /report/platform/mtbd/alerts/alertssummary/{vehicleRegNo} | Get | Yes | No | No |  |  | 27 | Not Required | done | Not Required
56 | /report/platform/mtbd/vehiclehealth/vehiclehealthsummary/{vehicleRegNo} | Get | Yes | No | No |  |  | 27 | Not Required | done | Not Required
57 | /report/platform/mtbd/delivery/vehicleusagesummary/{vehicleRegNo} | Get | Yes | No | No |  |  | 379
58 | /report/platform/farm/vehiclemovement/usagehours/{vehicleRegNo} | Get | No | Yes | No | 2017-06-19 | 2017-06-20
59 | /report/platform/farm/vehiclemovement/vehicleutilization/{vehicleRegNo} | Get | No | Yes | No | 2017-06-20 | 2017-06-20
60 | /report/platform/farm/vehiclemovement/enginehours/{vehicleRegNo} | Get | No | Yes | No | 2017-06-21 | 2017-06-22
61 | /report/platform/farm/alerts/vehiclealerts/{vehicleRegNo} | Get | No | Yes | No | 2017-06-21 | 2017-06-22
62 | /report/platform/farm/alerts/violation/{vehicleRegNo} | Get | No | Yes | No | 2017-06-22 | 2017-06-23
63 | UAT Testing |  |  |  |  | 2017-06-23 | 2017-06-27
Yes
No