## Sheet1
API Details Issues and Fixed
Service Name | Apis URL | Methods Name | Code Response | Status
Issues Raised By Greeshan Sir 27-04-2017
Driver | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/driverprofiles/driver | Post api/driverprofiles/driver | Issue resolved code on local not UAT not on SVN | Success
Driver | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/driverProfiles/{driverId} | Patch /driverProfiles/{driverId} | Issues with Db Fucntion | Fail
Expense | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/expenseCategory/{vehicleRegNo} | get /expenseCategory/{vehicleRegNo} | fixed , code on local , not on UAT | Success
Geofence | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/geofence/vehicles | GET /geofence/vehicles | usp_mobileapi_get_active_geofence_mapped_to_vehicle has issues. column "_geofencename" does not exist | Fail
Report | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api//report/platform/mtbd/vehiclemovement/enginerpm/{vehilceRegNo} | Get /report/platform/mtbd/vehiclemovement/enginerpm/{vehicleRegNo} | No Issues code on local not uat not on SVN | success
Forgot Password | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/LocationHistory/AP 09 KU 9999/?startDate=2016-01-01 00:00:00&endDate=2017-03-30 00:00:00 | Post ForgotPassword | issue in Db function | fail
Reset Password | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/resetPassword | Post resetPassword | issues in Db Function | fail
Issues raised by Anjani Mam
Report | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/report/platform/mtbd/vehiclemovement/enginerpm/AP 09 KU 9999?startdate=2017-02-02&enddate=2017-03-02 | Get /api/report/platform/mtbd/vehiclemovement/enginerpm//{vehicleRegNo}?startdate=2017-02-02&enddate=2017-03-02 | Fixed code on SVN not on UAT | success
Geofence | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/geofence | Post api/geofence | fixed code on local not on uat and svn | success
User Profile | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/profile/{userId} | patch /profile/{userId} | usp_mobileapi_update_user_details does not exist | fail
GeoFence | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api//geofence/{name}/vehicles | Get /geofence/{name}/vehicles | usp_mobileapi_get_vehicle_mapped_to_geofence column name change and registration columns missing in response | Fail
GeoFence | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/geofence/point11 | Patch I/api/geofence/{name} | code on local not on UAT and SVN | success
GeoFence | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/geofence/point11/vehicles | Put /api/geofence/{name}/vehicles | need to check db fucntion | fail
GeoFence | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/geofence/point11/vehicles?startdate=2017-02-01&enddate=2017-03-03 | api/geofence/point11/vehicles?startdate=2017-02-01&enddate=2017-03-03 | But it gives the response having endDate":"2017-03-02 00:00:00 | it is fine but need ali to reply about this
Report | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/report/platform/mtbd/vehiclemovement/enginerpm//TN 03 MM 1001/?startDate=2017-01-21 00:00:00&endDate=2017-01-29 00:00:00 | Get report/platform/mtbd/vehiclemovement/enginerpm//{vehicleRegNo}/ startDate=;&endDate=; | Fixed code on local not on UAT | success
Report | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/report/platform/mtbd/delivery/vehicleusage//{vehicleRegNo} | Get report/platform/mtbd/delivery/vehicleusage//{vehicleRegNo} | Fixed code on local not on UAT | success
Report | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/report/platform/mtbd/vehiclemovement/vehiclemovementreport/AP 09 KU 9999?startdate=2016-01-02&enddate=2017-04-02 | Get /api/report/platform/mtbd/vehiclemovement/vehiclemovementreport/AP 09 KU 9999?startdate=2016-01-02&enddate=2017-04-02 | Fixed : : [ : : : { : : : : "label":"DistanceTravelled", : : : : "data": : : : : [ : : : : : "12", It is not in “” as per swagger | Success response is ok , because in same class they are passing string int time many type of data so I had taken response as string for all .
Drivers | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/driverProfiles/{driverId} | delete /driverProfiles/{driverId} | is giving response as success even it has been deleted before or for non-existing id and that too spelling of success is not correct. | fail
Expense | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/expense/AP 09 KU 9999 | Put api/expense/{vehicleRegNo} | PUT data: { "label": "Salary", "value": "2300", "date": "2017-02-20 01:59:53", "createdBy": "168" } Response is:- { "label":"salary", "value":"2300", "date":"2017-02-20 01:59:53", "createdBy":"187" } | fail
vehicle alert | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/vehicleAlerts?startdate=2016-01-01&enddate=2017-03-01 | Get /vehicleAlerts/ | gives response for only 1 alert id i.e alert id 14. But as far as I know it should show last 24hrs alert populated and the date time mentioned in response is :"2016-09-06 16:11:27" for "vehicleRegNo":"AP 09 KU 9999 | fail
Report | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/reportSummary/platform/mtbd/health | /reportSummary/platform/mtbd/health | I think response is ok, but anjani mam is saying then please check
Geo Fence 9.01 | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/geofence | Post api/geofence
Geo Fence 9.02 | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/geofence | Get api/geofence
Geo Fence 9.03 | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/geofence/{name} | PATCH /geofence/{name}
Geo Fence 9.04 | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/geofence/{name}/vehicles | PUT /geofence/{name}/vehicles
Geo Fence 9.05 | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/geofence/{name} | DELETE /geofence/{name}
Geo Fence 9.06 | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/geofence/vehicles | GET /geofence/vehicles
Geo Fence 9.07 | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/geofence/{name}/vehicles | GET /geofence/{name}/vehicles
Report
Report 8.05 | GET https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/reportSummary/platform/{platform}/health | GET /reportSummary/platform/{platform}/health
Report 8.05 | GET https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/reportSummary/platform/{platform}/status | GET /reportSummary/platform/{platform}/status
Report 8.03 | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/reportsummary/platform/mtbd/vehiclemovement/speeddata/{vehicleRegNo} | GET /reportsummary/platform/mtbd/vehiclemovement/speeddata/{vehicleRegNo}
Report 8.03 | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/reportsummary/platform/mtbd/vehiclemovement/usagetime/{vehicleRegNo} | GET /reportsummary/platform/mtbd/vehiclemovement/usagetime/{vehicleRegNo}
Report 8.03 | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/reportsummary/platform/mtbd/vehiclemovement/enginerpm/{vehicleRegNo} | GET /reportsummary/platform/mtbd/vehiclemovement/enginerpm/{vehicleRegNo}
Report 8.03 | https://uat.mahindracloudlink.com/DigisenseMobileAPPAPI/api/reportsummary/platform/mtbd/vehiclemovement/vehiclemovementsummary/{vehicleRegNo} | GET /reportsummary/platform/mtbd/vehiclemovement/vehiclemovementsummary/{vehicleRegNo}